# Introduction: Using the Action Plan alongside the CSCP Self-Assessment Tool

This Action Plan template is designed to be used in conjunction with the CSCP Self-Assessment Tool to support continuous improvement in safeguarding practice.

Following completion of the self-assessment, organisations should use this document to capture, prioritise, and address any areas where practice does not fully meet the required standards. The Action Plan ensures that identified gaps are translated into clear, measurable actions that can be monitored over time.

To use this plan effectively:

- Review your completed self-assessment and identify any areas rated below the expected standard

- Record each gap clearly, ensuring that the underlying issue is accurately described

- Define specific actions that will address the gap, focusing on practical and achievable steps

- Assign clear ownership to a named lead officer responsible for delivery

- Set realistic timescales to ensure timely improvement

- Agree measurable outcomes so that progress and impact can be evidenced

- Regularly monitor and update progress, using supervision, audits, or performance reporting mechanisms

The Action Plan should be treated as a live document, reviewed routinely by managers and safeguarding leads. It should also support organisational assurance processes by providing clear evidence of how safeguarding standards are being strengthened and maintained.

By embedding this approach, organisations can demonstrate a commitment not only to compliance, but to ongoing learning, accountability, and high-quality safeguarding practice.

Common Pitfalls to Avoid

When using the CSCP Self-Assessment Tool and developing an Action Plan, organisations should be mindful of the following common pitfalls:

| - Lack of specificity Actions that are too vague, such as “improve training” or “review policy”, do not provide sufficient direction or accountability. Each action should clearly state what will be done and how. - Failure to identify root causes Recording symptoms rather than underlying issues, for example low training compliance without understanding why, can result in ineffective actions. - No clear ownership Actions without a named lead officer often led to delays or lack of progress. Accountability must be explicit. - Unrealistic or missing timescales Open-ended or overly ambitious deadlines reduce the likelihood of completion and weaken oversight. | - Lack of measurable outcomes Without defined success measures, it is difficult to evidence improvement or impact. - Treating the plan as a one-off exercise The Action Plan should be actively monitored and updated, rather than completed and filed away. - Insufficient management oversight Without regular review at a managerial or governance level, actions may lose priority. - Focus on compliance rather than impact Completing actions without considering whether they improve safeguarding practice can limit real change. |
| --- | --- |

| The sample Action Plan and template are designed to help you clearly record and manage any improvements identified through the CSCP Self-Assessment Tool. - The sample plan on this page shows how to turn identified gaps into clear actions with named leads, timescales, and measurable outcomes. - The template (see page 3) provides a simple structure that you can complete for your own organisation, helping you track progress and demonstrate improvement over time. |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Organisation: ABC Youth |  |  |  | Date of Self-Assessment: 1/4/2026 |  |  |  |
| Lead Officer: Sarah Bright |  |  |  | Review Period: 6 Months (Nov 2026) |  |  |  |
| Area for Improvement | Identified Gap | Action Required | Lead Officer |  | Timescale | Success Measures | Status |
| Staff Safeguarding Training | Not all staff are up to date with Level 2 safeguarding training | Audit training records and ensure all staff complete required training | Learning and Development Lead |  | Within 3 months | 100% staff compliant with training requirements | Not Started |
| Policy Awareness | Staff awareness of escalation procedures is inconsistent | Deliver briefing sessions and circulate updated Escalation & Resolution Policy | Safeguarding Lead |  | Within 2 months | Staff survey evidences improved awareness, attendance records maintained | In Progress |
| Recording and Documentation | Case records lack consistency in quality and detail | Introduce standardised recording template and provide guidance | Team Manager |  | Within 4 months | Audit shows improved recording quality and completeness | Not Started |
| Multi-Agency Working | Limited evidence of effective information sharing | Reinforce expectations through team meetings and supervision | Service Manager |  | Ongoing | Increased documented multi-agency communication in case audits | In Progress |
| Supervision and Oversight | Supervision records do not consistently reflect safeguarding discussions | Update supervision template to include mandatory safeguarding section | Team Manager |  | Within 2 months | Supervision audits show safeguarding is routinely discussed | Not Started |

| Monitoring and Review | Sign-Off |  |  |  |
| --- | --- | --- | --- | --- |
| Progress Review Frequency: Monthly Reported to: Senior Leadership Team Method of Monitoring: - Supervision audits - Training compliance reports - Staff feedback | Name | Role | Signature | Date |
|  | Sarah Bright | Safeguarding Lead | S.Bright | 05/04/2026 |
|  | Jonathan Brown | Service Manager | Jonathan Brown | 05/04/2026 |

| Organisation: |  |  |  | Date of Self-Assessment: |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Lead Officer: |  |  |  | Review Period: |  |  |  |
| Area for Improvement | Identified Gap | Action Required | Lead Officer |  | Timescale | Success Measures | Status |

| Monitoring and Review | Sign-Off |  |  |  |
| --- | --- | --- | --- | --- |
| Progress Review Frequency: Weekly/Fortnightly/Monthly Reported to: Method of Monitoring: | Name | Role | Signature | Date |